## Quiz
Quiz Plan |  |  | Last updated:
|  |  | Lessons per week: |  | 2
|  |  | Homework per week : |  | 3
Task | Duration (hours) | Duration (Days) | Start | End | Completed | Total Duration | Difference (Days) | Comments
Design questions | 1 | 1.4 | 2009-10-03 | 2009-10-04 09:36 | 2009-10-04 | 1 | 0.4
Create questions page | 6 | 8.4 | 2009-10-05 | 2009-10-13 09:36 | 2009-10-15 | 10 | -1.6 | The questions page took longer as the drop down menus were more difficult than expected
Get feedback | 1 | 1.4 | 2009-10-16 | 2009-10-17 09:36 | 2009-10-17 | 1 | 0.4
Make updates | 2 | 2.8 | 2009-10-18 | 2009-10-20 19:12 | 2009-10-19 | 1 | 1.8 | Work was done slightly quicker than expected. It was not as difficult as I have become more skilled with excel
Create scoring system | 10 | 14 | 2009-11-03 | 2009-11-17 | 2009-11-20 | 17 | -3 | I had to wait for help from my teacher as I found VLOOKUPs hard to understand. I also had football training which meant that i could not attend extra sessions till later on in the week.
Do analysis | 8 | 11.2 | 2009-11-21 | 2009-12-02 04:48 | 2009-12-02 | 11 | 0.2
Create results page | 6 | 8.4 | 2009-12-03 | 2009-12-11 09:36 | 2009-12-09 | 6 | 2.4 | I did extra homework to try and catch up.
Get feedback | 1 | 1.4 | 2009-12-10 | 2009-12-11 09:36 | 2009-12-10 | 0 | 1.4 | I got feedback from my test buddy on the same day i finished.
make updates | 2 | 2.8 | 2009-12-11 | 2009-12-13 19:12 | 2009-12-15 | 4 | -1.2 | I had a lot of updates to make to my scoreing system. It did not display fitness result correctly for low fitness
Update plan and soruces table | 1 | 1.4 | 2009-12-16 | 2009-12-17 09:36 | 2009-12-17 | 1 | 0.4
Contingency | 4 | 5.6 | 2009-12-18 | 2009-12-23 14:24 |  | 0 | 0
TOTAL |  | 58.8 |  |  |  | 52 | 6.8
Formulas:
End = [Start]+[Duration (Days)]
Start = IF([Completed, row above]="",[End, row above]+1,[Completed, row above]+1)