Performance review

Through the course i have followed my plan as can be seen from my project diary. I did each task in the correct order apart from the “make a catch” section. I did this before my playlist as I had difficulty with the database part of the work and needed extra help. Rather than not do anything at home i decided to start my make a catch. That way i did not waste any time.

I had trouble coming up with a good design at the beginning. My first two designs were very basic as i was learning a lot of new skills. I only thought I would do a draft version and the final version when in fact I did two draft versions. This put me behind schedule by 2 weeks and ate up a lot of my contingency time. I also had trouble doing the database part (as already stated). I had to come after school to get extra help from my teacher. This delayed the playlist and meant that i was working on the play list and make a catch at the same time.

As I was behind I decided to do extra work over the Spring half term. I spent two whole days working on my ICT project and caught up a lot of the missing time. At the end of this holiday I was back on track with my plan. I also had to come back afterschool a few times in order to get extra help for my database.

I feel I planned out my time well and apart from the database and my original design my estimates were fairly accurate.  When i did fall behind i did extra work to catch up. I added contingency time (about 1 week) which i ended up needing. I also factored in my holiday to Florida over the Easter holidays  and made sure i did extra homework the weeks before. I also did less homework when my English coursework was due. As I knew about this when i made my plan i factored that in and did no ICT homework for 2 weeks just after Christmas.